## General Aspects
Procurement Plan |  |  | Credit No : 8466 AL | Project ID P144688
Project Name: Albania Health System Improvement Project
I. General
Agreed date of procurement Plan
Original: December 23, 2014
Update: December 1, 2015 |  |  | No-Objection date: December 1, 2015
Date of General Procurement Notice: Published on UNDB online on __ December 2015
II. Goods and Works
1. Prior Review Threshold: Procurement Decisions subject to Prior Review by the Bank as stated in Appendix 1 to the Guidelines for Procurement:
| Procurement Method | Threshold (USD) | Threshold (EUR Eqv.)approx. | Prior Review
1 | ICB (Goods) | ≥ 1,000,000 | ≥ 900,900 | All
2 | NCB (Goods) Packages | <1,000,000 | < 900,900 | First contract
3 | ICB (Works) Packages | ≥ 5,000,000 | ≥ 4,720,000 | First contract
4 | NCB (Works) Packages | <10,000,000 | < 4,720,000 | First contract
5 | Shopping (Goods and Works) | ≤ 100,000 | ≤ 90,090 | First contract for goods
6 | Direct Contracting | "none" | "none" | US$ ≥ 60,000 or EUR 54,054, subject to justification
All TORs subject to prior review.
2. Manual: The client will prepare a Project Operation Manual to be used/applied under the project.
III. Selection of Consultants
1. Prior Review Threshold: Selection decisions subject to Prior Review by Bank as stated in Appendix 1 to the Guidelines Selection and Employment of Consultants:
| Selection Method | Threshold (USD) | Threshold (EUR Eqv.)approx. | Prior Review
1. | Consultant (Firms) | ≥ 300,000 | ≥ 280,000 | First QCBS and all above US$ 500,000; First CQS
2 | Consultant (Individual) | None | None | All US$ ≥ 200,000 or EUR ≥ 180,180
3 | Single Source (Firms and Individuals)* | None* | None* | US$ ≥ 5,000 or EUR 4,500
| ToRs for Consulting Contracts |  |  | All
* Subject to justification in accordance para.3.7 and para. 3.8 of the Procurement nd Consultant Guideline, respectively
2. Short list comprising entirely of national consultant: Short list of consultants for services, estimated to cost less thant US$300,000 equivalent per contract,
may comprise entirely of national consultants in accordance with the provisions of paragraph 2.7 of the Consultants Guidelines.
Detailed procurement activities for goods and works, and consulting services are enclosed in the next excel spread sheet

## Procurement Plan
Project Name: Albania Health System Improvement Project
Project ID Number: P144688
Credit No: 8466 AL
Original Date: December 23, 2014
Update date: October 2, 2015, October 9, 2015 and December 23, 2015
1 | 2 | 3 | 4 | 5 | 6 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[6 empty] | Estimated Date of Initial TOR for the activity | Bank's "No-Objection" to the ToR | Publication of the Request of Expression of Interest | Expected EoI Submission Date | Submission to the Bank of Shortlist and draft RFP | Bank's "No-objection" to the RFP and shortlist | Technical Evaluation Report | Bank's no-objection on Technical Evaluation Report | Submission of Final Evaluation Report | Draft Negotiated Contract | Bank's "No-Objection" | Expected Contract Signing | Expected Contract Completion Date | Contractor's name and address | Contract Amendment (if any)
Reference | Package Nr. | Description of Contract Package | Procurement Type | Procurement method | Year | Estimated Date of submission of BD/ IFB/ ITQ and Technical Specification | Bank's "No-Objection" to the BD/ IFB / ITQ | Publication of the IFB/ issuing ITQ | Expected date of Bid / Quotations received | Evaluation Report | Bank's "No-objection" to the Evaluation Report |  |  |  | Contract Award/ Letter of Acceptance |  | Expected Contract Signing | Expected Contract Completion Date | Contractor's name | Contract Amendment (if any)
Component 1: Improving Hospital Services (Euro 15.10 million ; US$ 18.80 million)
Sub-component 1.1: Strengthening the Albanian Network of Hospital Services (Euro 2.72 million; US$ 3.4 million equivalent)
HSIP/CS/CQS/05-2015 | A.1.1.1 | Review of the Existing Hospital Master Plan (Health Facility Rationalization Plan) | CS | CQS | 1 | 2015-11-10 | 2015-12-20 | 2015-12-30 | 2016-01-14 | 2016-01-29 | n/a | n/a | n/a |  | 2016-02-18 | n/a | 2016-03-04
| A.1.1.2 | Review of the hospital legal framework including the establishment and implementation of training program for Board of Directors | CS | QCBS | 1 | 2015-12-20 | 2016-01-09 | 2016-01-19 | 2016-02-18 | 2016-03-29 | 2016-04-13 | 2016-05-11 | 2016-05-21 |  | 2016-06-10 | 2016-06-20 | 2016-06-30 | 2016-11-09
| A.1.1.3 | Legal services for non-profit community based organizations | CS | IC | 2 | 2017-01-15 | 2017-02-04 | 2017-02-14 | 2017-03-01 | 2017-03-16 | n/a | n/a | n/a |  | 2017-04-05 | n/a | 2017-04-10
| A.1.1.4 | Establish an Accountability Tracking system using M&E indicators: to develop M&E accountability tracking system | CS | CQS | 2 or 3 | 2018-03-10 | 2018-03-30 | 2018-04-09 | 2018-04-24 | 2018-05-09 | n/a | n/a | n/a |  | 2018-05-29 | n/a | 2018-06-13
| A.1.1.5 | TA to the MoH Management on Health Reform | CS | CQS |  | 2017-01-15 | 2017-02-24 | 2017-03-06 | 2017-03-21 | 2017-04-05 | n/a | n/a | n/a |  | 2017-04-25 | n/a | 2017-05-10 | 2017-09-19
| A.1.1.6 | Improving patient management, facility management and accountability: International TA using administrative data to improve quality and performance | CS | IC | 3 | 2019-06-01 | 2019-06-11 | 2019-06-21 | 2019-07-06 | 2019-07-21 | n/a | n/a | n/a |  | 2019-08-10 | n/a | 2019-08-15
| A.1.1.7 | Improving patient management, facility management and accountability: International TA social accountability mechanisms in the EU and globally | CS | CQS | 2 | 2018-06-01 | 2018-06-21 | 2018-07-01 | 2018-07-16 | 2018-07-31 | n/a | n/a | n/a |  | 2018-08-20 | n/a | 2018-08-25
| A.1.1.8 | QSUT international management team support | CS | QCBS | 1 | 2017-06-01 | 2017-06-21 | 2017-07-01 | 2017-07-31 | 2017-09-09 | 2017-09-24 | 2017-10-22 | 2017-11-01 |  | 2017-11-21 | 2017-12-01 | 2017-12-11 | 2018-04-22
HSIP/CS/IC/04-2015 | A.1.1.9 | QSUT management assessment & preparation of TOR for the international management team | CS | IC |  | 2017-10-01 | 2017-10-11 | 2017-10-21 | 2017-11-05 | 2017-11-20 | n/a | n/a | n/a |  | 2017-12-10 | n/a | 2017-12-15
| A.1.1.10 | Public Communication Campaign on Hospital Master Plan | CS | CQS |  | 2018-04-25 | 2018-05-05 | 2018-05-15 | 2018-05-30 | 2018-06-14 | n/a | n/a | n/a |  | 2018-07-04 | n/a | 2018-07-09
HSIP/CS/CQ/03-2015 | A.1.1.11 | Communication campaign for hospitals’ reform | CS | CQS |  | 2015-11-15 | 2015-11-25 | 2015-12-05 | 2015-12-20 | 2016-01-04 | n/a | n/a | n/a |  | 2016-01-24 | n/a | 2016-01-29
HSIP/CS/CQ/02-2015 | A.1.1.12 | Developing National Health Accounts | CS | CQS |  | 2015-10-20 | 2015-10-30 | 2015-11-09 | 2015-11-24 | 2015-12-09 | n/a | n/a | n/a |  | 2015-12-29 | n/a | 2016-01-03
Sub-component 1.2: Improving hospital infrastructure and the management of medical equipment (Euro 12.38 million; US$ 15.40 million equivalent)
HSIP/CS/CQ/04-2015 | A.1.2.1 | Technical assessment, architectonic design, specifications, estimated cost and supervision of civil works/ medical equipment and Furniture’s Installation of existing pediatric hospital buildings | CS | CQS |  | 2015-12-20 | 2016-01-09 | 2016-01-19 | 2016-02-18 | 2016-03-29 | n/a | n/a | n/a |  | 2016-04-18 | n/a | 2016-04-23 | 2016-08-11
| A.1.2.2 | Rehabilitation of Pediatric Hospital (QSUT) | CW | ICB |  | 2016-04-30 | 2016-05-10 | 2016-05-12 | 2016-06-11 | 2016-07-21 | 2016-07-31 | 2016-08-30 | n/a |  | 2016-08-05 | 2016-08-15 | 2016-08-20 | 2016-12-08
| A.1.2.3 | Rehabilitation of infrastructure of selected hospitals under HMP | CW | NCB |  | 2017-04-30 | 2017-05-10 | 2017-05-12 | 2017-06-11 | 2017-07-21 | 2017-07-31 | 2017-08-30 | n/a |  | 2017-08-05 | 2017-08-15 | 2017-08-20 | 2017-12-08
| A.1.2.4 | Medical Equipment for Hospitals | G | ICB |  | 2016-10-30 | 2016-11-09 | 2016-11-11 | 2016-12-11 | 2017-01-20 | 2017-01-30 | 2017-03-01 | n/a |  | 2017-02-04 | 2017-02-14 | 2017-02-19 | 2017-04-26
| A.1.2.5 | Biomedical Engineering Application Software | G | SH |  | 2017-03-01 | 2017-03-11 | 2017-03-26 | 2017-04-10 | 2017-05-20 | n/a | 2017-06-19 | n/a |  | 2017-05-25 | n/a | 2017-05-25 | 2017-06-24
| A.1.2.6 | Medical Equipment Management Team to provide TA, Training & Study Tours | CS | CQS |  | 2016-09-01 | 2016-09-11 | 2016-09-21 | 2016-10-06 | 2016-10-21 | n/a | n/a | n/a |  | 2016-11-10 | n/a | 2016-11-15 | 2017-03-27
Component 2: Expanding the Health Management Information System (Euro 13.60 million; US$ 16.95 million equivalent)
Sub-component 2.1: | HMIS/eHealth Foundational Activities and Establishing the National Health Information Center (NHIC) (Euro 2.68 million; US$ 3.35 million equivalent)
| A.2.1.1 | Creating the Master Plan for HMIS/eHealth Activities (2016-2020) & Health Data Dictionary | CS | CQS |  | 2015-11-15 | 2015-11-30 | 2015-12-02 | 2015-12-17 | 2016-01-14 | n/a | n/a | n/a |  | 2016-02-03 | n/a | 2016-02-08 | 2016-08-02
HSIP/CS/CQ/01-2015 | A.2.1.2 | Project Architectonic Design, Inspection and Supervision of Civil Works for Reconstruction of Design and Supervision of National Health Information Center (NHIC) - (First "CQS" Contract) | CS | CQS |  | 2015-09-25 | 2015-10-28 | 2015-12-01 | 2015-12-21 | 2016-01-18 | 2016-01-23 | n/a | n/a |  | 2016-02-02 | 2016-02-12 | 2016-02-14 | 2016-08-08
| A.2.1.3 | Upgrading of the NHIC building | CW | NCB |  | 2015-12-20 | 2015-12-30 | 2016-01-01 | 2016-01-31 | 2016-03-11 | n/a | n/a | n/a |  | 2016-03-31 | n/a | 2016-04-05 | 2016-07-24
| A.2.1.4 | Creating the first version of the Essential Registries for HMIS, including implementation and update mechanisms populating and validating registries | CS | CQS |  | 2017-07-05 | 2017-07-15 | 2017-07-17 | 2017-08-01 | 2017-08-31 | n/a | n/a | n/a |  | 2017-09-20 | n/a | 2017-09-25
| A.2.1.5 | Design services for Health Date Center architecture & topology, CRM, help desk/user support center & training center and CRM system | CS | QCBS |  | 2016-02-01 | 2016-02-21 | 2016-03-02 | 2016-04-01 | 2016-05-11 | 2016-05-26 | 2016-06-23 | 2016-07-03 |  | 2016-07-23 | 2016-08-02 | 2016-08-12 | 2016-12-22
| A.2.1.6 | Health Data Center IT equipment | G | ICB |  | 2016-09-10 | 2016-09-20 | 2016-09-22 | 2016-11-21 | 2016-12-21 | 2016-12-31 | n/a | n/a |  | 2017-01-15 | 2017-01-25 | 2017-02-09 | 2017-03-11
| A.2.1.7 | Design of Biomedical Equipment Maintenance Unit and IT equipment maintenance | CS | IC |  | 2016-05-01 | 2016-05-11 | 2016-05-21 | 2016-06-05 | 2016-06-20 | n/a | n/a | n/a |  | 2016-07-10 | n/a | 2016-07-15
| A.2.1.8 | Furniture and Furnishing for NHIC | G | NCB |  | 2016-05-01 | 2016-05-16 | 2016-05-18 | 2016-07-02 | 2016-08-01 | 2016-08-21 | n/a | n/a |  | 2016-08-23 | n/a | 2016-09-07 | 2016-10-07
| A.2.1.9 | IT Capacity building | CS | CQS |  | 2016-09-10 | 2016-09-20 | 2016-09-22 | 2016-10-07 | 2016-11-06 | n/a | n/a | n/a |  | 2016-11-26 | n/a | 2016-12-01
Sub-component 2.2: Implementing Regional Hospital Information Systems (Euro 9.30 million; US$ 11.60 million equivalent)
| A.2.2.1 | Requirements Study & Prepare Tender | CS | CQS |  | 2016-05-01 | 2016-05-16 | 2016-05-18 | 2016-06-02 | 2016-06-30 | 2016-07-05 | n/a | n/a |  | 2016-07-15 | 2016-07-25 | 2016-07-27 | 2017-01-19
| A.2.2.2 | Supply and Installation of Regional Hospital Information System (RHIS) including training | G | ICB |  | 2017-11-10 | 2017-11-20 | 2017-11-22 | 2018-01-21 | 2018-02-20 | 2018-03-02 | n/a | n/a |  | 2018-03-17 | 2018-03-27 | 2018-04-11 | 2018-05-11
Sub-component 2.3 Implementing a new Health Insurance Information System (HIIS) for the Health Insurance Fund (HIF) (Euro 1.62 million; US$ 2.0 million equivalent)
| A.2.3.1 | Health Insurance Information System (HIIS) procurement: Software, Networking Hardware, Main hardware shared at NHIC | G | ICB |  | 2018-01-10 | 2018-01-20 | 2018-01-22 | 2018-03-23 | 2018-04-22 | 2018-05-02 | n/a | n/a |  | 2018-05-17 | 2018-05-27 | 2018-06-11 | 2018-07-11
| A.2.3.2 | Capacity building: Training on HIF business processes as a factory & automated claims shop | CS | IC |  | 2018-01-01 | 2018-01-11 | 2018-01-21 | 2018-02-05 | 2018-02-20 | n/a | n/a | n/a |  | 2018-03-12 | n/a | 2018-03-17
| A.2.3.3 | Requirements Study, High-level Conceptual Design and Preparation of Tender of HIIS | CS | CQS |  | 2018-05-01 | 2018-05-11 | 2018-05-21 | 2018-06-05 | 2018-06-20 | n/a | n/a | n/a |  | 2018-07-10 | n/a | 2018-07-15
Component 3: Improving the Health Financing System (Euro 2.40 million equivalent; US$ 3.0 million equivalent)
Sub-component 3.1: Payment Reform (Euro 1.70 million; US$ 2.10 million equivalent)
| A.3.1.1 | Develop annual business plans, automization strategy, monitoring indicators and provider Payment Reform in Primary Health Care including workshops and study tours | CS | QCBS | 1 | 2016-03-01 | 2016-03-21 | 2016-03-31 | 2016-04-30 | 2016-06-09 | 2016-06-24 | 2016-07-22 | 2016-08-01 |  | 2016-08-21 | 2016-08-31 | 2016-09-10 | 2017-01-20
| A.3.1.2 | Provider Payment Reform in Hospital, inclidog study tours in Europe and high level workshops in Europe for 50 people, 2 days | CS | CQS | 1 | 2016-01-01 | 2016-02-10 | 2016-02-20 | 2016-03-06 | 2016-03-21 | n/a | n/a | n/a |  | 2016-04-10 | n/a | 2016-04-25
| A.3.1.3 | Develop DRG hospital funding and impact model at HIF, annual business plans, monitoring indicators and provider Payment Reform in Hospitals | CS | CQS | 1 | 2016-07-01 | 2016-07-11 | 2016-07-21 | 2016-08-05 | 2016-08-20 | n/a | n/a | n/a |  | 2016-09-09 | n/a | 2016-09-14
| A.3.1.4 | Supply & installation of Financial Management System Software in about 100 PHCs | G | NCB | 1 | 2016-06-01 | 2016-06-11 | 2016-06-13 | 2016-08-12 | 2016-09-11 | n/a | n/a | n/a |  | 2016-10-01 | n/a | 2016-10-06 | 2016-11-05
| A.3.1.5 | Review of coding system for diagnosis and procedures of pharmaceutical, PHCs and hospitals | CS | CQS | 1 | 2016-06-01 | 2016-06-11 | 2016-06-21 | 2016-07-06 | 2016-07-21 | n/a | n/a | n/a |  | 2016-08-10 | n/a | 2016-08-15
| A.3.1.6 | DRG Grouper Software | G | ICB | 2 or 3 | 2018-11-01 | 2018-11-11 | 2018-11-13 | 2019-01-12 | 2019-02-11 | 2019-02-21 | n/a | n/a |  | 2019-03-08 | 2019-03-18 | 2019-04-02 | 2019-05-02
| A.3.1.7 | Develop P4P for performance models and introduce P4P with evaluation of the pilots | CS | CQS | 4 | 2018-06-01 | 2018-06-11 | 2018-06-21 | 2018-07-06 | 2018-07-21 | n/a | n/a | n/a |  | 2018-08-10 | n/a | 2018-08-15
| A.3.1.8 | Develop quality assurance systems in conjunction with new payment systems | CS | IC | 4 | 2019-05-01 | 2019-05-11 | 2019-05-21 | 2019-06-05 | 2019-06-20 | n/a | n/a | n/a |  | 2019-07-10 | n/a | 2019-07-15
Sub-component 3.2: | Support to the HIF for strategic purchasing, improved coverage and pharmaceutical reform (Euro 0.70 million; US$ 0.90 million equivalent)
| A.3.2.1 | Restructuring of existing reimbursed drug list & development HTA capacity for staff in chage of reviewing submissions from companies that seek reimbursement for medicine (MOH, HIF) | CS | CQS | 1 | 2017-01-01 | 2017-01-11 | 2017-01-21 | 2017-02-05 | 2017-02-20 | n/a | n/a | n/a |  | 2017-03-12 | n/a | 2017-03-17
| A.3.2.2 | Development generic drugs promotion campaign & training of staff in regional committees | CS | CQS | 2 | 2018-01-01 | 2018-01-11 | 2018-01-21 | 2018-02-05 | 2018-02-20 | n/a | n/a | n/a |  | 2018-03-12 | n/a | 2018-03-17
| A.3.2.3 | Piloting expanded coverage of outpatient drug benefit package | CS | CQS | 3 | 2019-01-01 | 2019-01-11 | 2019-01-21 | 2019-02-05 | 2019-02-20 | n/a | n/a | n/a |  | 2019-03-12 | n/a | 2019-03-17
| A.3.2.4 | Development of Health Insurance Organization "Road Map" including study tours | CS | CQS |  | 2020-06-01 | 2020-06-11 | 2020-06-21 | 2020-07-06 | 2020-07-21 | n/a | n/a | n/a |  | 2020-08-10 | n/a | 2020-08-15
| A.3.2.5 | Training abroad of HI organization experts, management/claims auditing expeerts, fraud detection experts, management dashboards | CS | CQS |  | 2019-01-01 | 2019-02-10 | 2019-02-20 | 2019-03-07 | 2019-03-22 | n/a | n/a | n/a |  | 2019-04-11 | n/a | 2019-04-26
| A.3.2.6 | Performance Measurement System | CS | CQS |  | 2019-02-01 | 2019-02-11 | 2019-02-21 | 2019-03-08 | 2019-03-23 | n/a | n/a | n/a |  | 2019-04-12 | n/a | 2019-04-17
| A.3.2.7 | Moving to general revenue/expenditure and revenue model including training/workshop | CS | CQS |  | 2019-03-01 | 2019-03-11 | 2019-03-21 | 2019-04-05 | 2019-04-20 | n/a | n/a | n/a |  | 2019-05-10 | n/a | 2019-05-15
Component 4: | Monitoring, Evaluation and Project Management (Euro 0.92 million equivalent; US$ 1.15 million equivalent)
HSIP/CS/IC/01-2015 | A.4.1.1 | Project Manager | CS | IC |  | 2015-06-01 | 2015-07-08 | 2015-07-09 | 2015-08-04 | 2015-08-10 | 2015-08-17 | n/a | n/a |  | n/a | 2015-08-26 | 2015-08-26 | 2021-02-28 | Mrs. Blerina Dudushi Rruga “Sami Frasheri”, Pallati Vortek, Sh A, Apt 19, Tirana 1001, Albania, mobile: 67 200 4 935 , blerinadudushi@gmail.com
| A.4.1.2 | Office Assistant | CS | IC |  | 2016-01-01 | 2016-01-11 | 2016-01-21 | 2016-02-05 | 2016-02-20 | 2016-03-01 | n/a | n/a |  | n/a | n/a | 2016-03-11
HSIP/CS/IC/02-2015 | A.4.1.3 | Procurement Consultant | CS | IC |  | 2015-06-01 | 2015-07-08 | 2015-07-09 | 2015-08-04 | 2015-08-10 | 2015-08-12 | n/a | n/a |  | n/a | 2015-08-26 | 2015-08-26 | 2021-02-28 | Mrs. Elma Dogani – Procurement Specialist Rr: “ Haxhi H Dalliu”, Pll.184/9, Apt.7, Tirana, Albania, e-mail:elmadogani@gmail.com, mobile: 0682449014
HSIP/CS/IC/03-2015 | A.4.1.4 | Financial Management Consultant | CS | IC |  | 2015-06-01 | 2015-07-08 | 2015-07-09 | 2015-08-04 | 2015-08-10 | 2015-08-12 | n/a | n/a |  | n/a | 2015-08-26 | 2015-08-26 | 2021-02-28 | Mrs. Daniela Gjylameti Rruga "Shemsi Haka", Pll. MATRIX, Tirana, Albania, mobile: 0692512313
| A.4.1.5 | IT Consultant | CS | IC |  | 2016-01-01 | 2016-01-11 | 2016-01-21 | 2016-02-05 | 2016-02-20 | n/a | 2016-03-01 | n/a |  | n/a | n/a | 2016-03-21
| A.4.1.6 | Supervising Engineer (2) | CS | IC |  | 2017-01-01 | 2017-01-11 | 2017-01-21 | 2017-02-05 | 2017-02-20 | n/a | 2017-03-02 | n/a |  | n/a | n/a | 2017-03-22
| A.4.1.7 | Office equipment for PCU | G | SH
HSIP/G/SH/01-2015 | A.4.1.7 (a) | IT Equipment for PCU staff (first "shopping" contract) | G | SH |  | 2015-09-25 | 2015-11-04 | 2015-11-10 | 2015-11-25 | 2015-12-01 | 2015-12-11 | n/a | n/a | n/a | 2015-12-13 | n/a | 2015-12-13 | 2016-01-02
HSIP/G/SH/02-2015 | A.4.1.7 (b) | Project Accounting Software Application | G | SH |  | 2015-11-25 | n/a | 2015-12-15 | 2015-12-30 | 2016-01-09 | n/a | n/a | n/a | n/a | 2016-01-11 | n/a | 2016-01-11 | 2016-01-26
HSIP/G/SH/03-2015 | A.4.1.7 (a) | Furniture for PCU staff offices (2) | G | SH |  | 2015-11-25 | n/a | 2015-12-01 | 2015-12-16 | 2015-12-21 | n/a | n/a | n/a | n/a | 2015-12-23 | n/a | 2015-12-23 | 2016-01-02
| A.1.1.8 | Operating Cost | bar: 2015-11-10
Front-end Fee
Unalocated
Formulas:
Contract Award/ Letter of Acceptance = [Evaluation Report]+20
Expected Contract Signing = [Contract Award/ Letter of Acceptance]+15
Expected Contract Signing = [Contract Award/ Letter of Acceptance]
Expected Contract Completion Date = [Expected Contract Signing]+(22*6)
Expected Contract Completion Date = [Expected Contract Signing]+66